## Summary
Wimborne Model Town River System

Version 0.2, 13th April 2017

Functional Requirements Index

Phase 1 – Cleaning, Clearing and Flow Improvement

Phase 2 – Improve Water Clarity and the WMT as a Visitor Attraction

Phase 3 – Reduce the Dependence of the River System on Mains Water

Phase 4 – Automate the System

Phase 5 – Expand Rainwater Storage and Irrigation

Phase 6 – Stored Water Balancing Between Storage Sites

This work is licensed under the Creative Commons Attribution-NonCommercial-ShareAlike 4.0 International License. To view a copy of this license, visit http://creativecommons.org/licenses/by-nc-sa/4.0/.

## Phase 1
Functional Requirements
Phase 1 – Cleaning, Clearing and Flow Improvement

Requirement Numbers		Requirement	Priority	Type	Status
Source	Derived
2.1.1		Maintain a water flow in the river system at all times; sufficient to ensure water clarity and inhibit algae growth.	1	Essential	In progress
1.2	1.1	The Project shall remove obstructions to water flow in the river.	1	Essential	Complete
1.3	1.2	The Project shall remove obstructions to water flow in the plumbing system.	1	Essential	Complete
1.3	1.3	The Project shall provide a more powerful, more efficient, variable speed pump.	1	Essential	Complete
2.1.2		Reduce the dependence of the river system on mains water.	1	Essential	In progress
1.1	1.4	The system shall maintain the integrity of the river bed by stopping all identifiable leaks.	1	Essential	Complete 1

Notes:	1	This Requirement has essentially been fulfilled, but it is recognised that it is an ongoing maintenance task which will require attention at least every Winter.

## Phase 2
Functional Requirements
Phase 2 – Improve Water Clarity and the WMT as a Visitor Attraction

Requirement Numbers		Requirement	Priority	Type	Status
Source	Derived
2.1.1		Maintain a water flow in the river system at all times; sufficient to ensure water clarity and inhibit algae growth.	1	Essential	In progress
2.1	2.1	The system shall provide a filter cage at the inlet of the pump to prevent large debris from being drawn into the pump impeller.	1	Essential	Complete
2.2	2.2	The system shall provide a natural water filtration system in the form of a bog garden to mechanically and biologically condition the water passing through it.	1	Essential	Complete
2.3	2.3	The system shall provide a pre-sump filter to prevent large debris from reaching the pump impeller inlet filter.	1	Essential	In progress
2.1.3		Enhance WMT as a Visitor Attraction.	1	Essential	In progress
2.2	2.4	A variety of suitable plants shall be planted in the bog garden to create a new eco-system.	1	Essential	In progress
2.2	2.4.1	The locations of all plants shall be documented.	1	Essential	In progress

## Phase 3
Functional Requirements
Phase 3 – Reduce the Dependence of the River System on Mains Water

Requirement Numbers		Requirement	Priority	Type	Status
Source	Derived
2.1.2		Reduce the dependence of the river system on mains water.	1	Essential	In progress
3.2	3.1	Water butts shall be provided to store excess water from the river, so that the level may be replenished as necessary.	1	Essential	In progress
3.1	3.1.1	The necessary piping shall be provided between the water butts and the river.	1	Essential	In progress
3.3	3.1.2	A method of transferring water from the sump to the butts shall be provided. 1	1	Essential	In progress
3.3	3.1.3	A stop-tap shall be provided to control the flow of water from the butts to the river.	1	Essential	In progress
3.3	3.1.4	An overflow facility shall be provided for each butt.	2	Desirable	Not started

Notes:	1	If practicable, the existing sump pump should be re-used for this purpose.

## Phase 4
Functional Requirements
Phase 4 – Automate the System

Requirement Numbers		Requirement	Priority	Type	Status
Source	Derived
2.1.1		Maintain a water flow in the river system at all times; sufficient to ensure water clarity and inhibit algae growth.	1	Essential	In progress
4.1	4.1	Capture Requirement for the Phase.	2	Desirable	This document
4.2	4.2	Develop high level design for the system.	2	Desirable	Not started
4.3	4.3	The system shall provide a fully automated control for all aspects of the river system.	2	Desirable	Not started
4.3	4.3.1	Automated control of the system shall utilise embedded computer techniques.	2	Desirable	Not started
4.3	4.3.1.1	The system shall allow for manual override of the controlling functions.	2	Desirable	Not started
	4.3.1.2	A test mode shall be provided.	2	Desirable	Not Started
4.3	4.3.1.3	A Graphical User Interface (GUI) shall be provided.	2	Desirable	Not started
2.1.3		Enhance WMT as a Visitor Attraction.	2	Essential	Not started
	4.4	Educational displays shall be provided to inform visitors.	2	Desirable	Not started

## Phase 5
Functional Requirements
Phase 5 – Expand Rainwater Storage and Irrigation

Requirement Numbers		Requirement	Priority	Type	Status
Source	Derived
2.2.2		Expand rain water harvesting, storage and irrigation feeds to suit needs of river / gardens.	2	Desirable	Not started
-	5.1	Flexible hoses and ‘soaker’ hoses shall be provided to allow gardeners to irrigate plants.	2	Desirable	In progress
-	5.1.1	A means of controlling the flow of water to the soaker hoses shall be provided.	2	Desirable	Not started

## Phase 6
Functional Requirements
Phase 6 – Stored Water Balancing Between Storage Sites

Requirement Numbers		Requirement	Priority	Type	Status
Source	Derived
2.2.3		Stored water “balancing” between storage sites.	2	Desirable	Not started
-	6.1	Additional rainwater butts shall be located in suitable places to harvest water from the roofs of the WMT buildings.	2	Desirable	Not started
-	6.1.1	A means of balancing the water levels in the rainwater butts shall be provided.	2	Desirable	Not started