In progress
This requirement appears in multiple places (also in Phase 4) yet isn’t specified precisely. Does this requirement include enhancing WMT’s educational value?
This requirement appears in multiple places (also in Phase 4) yet isn’t specified precisely.Does this requirement include enhancing WMT’s educational value?
A functional overview diagram of how the river control system works shall be provided.
The GUI shall offer full manual override features in an easily accessible place for the event of a software failure.
Desirable
The GUI shall offer full manual override features for use in the event of a software failure.
The system shall allow for manual override of the controlling functions.
The system shall provide a fully automated control for all aspects of the river system.
Version 0.2, 13th April 2017
The GUI shall have all of its features presented in one tabbed window for easy of use.
The automated control system MUST have an emergency shut-off feature.
## Summary
Wimborne Model Town River System

Version 0.3, 19th April 2017

Functional Requirements Index

Phase 1 – Cleaning, Clearing and Flow Improvement

Phase 2 – Improve Water Clarity and the WMT as a Visitor Attraction

Phase 3 – Reduce the Dependence of the River System on Mains Water

Phase 4 – Automate the System

Phase 5 – Expand Rainwater Storage and Irrigation

Phase 6 – Stored Water Balancing Between Storage Sites

This work is licensed under the Creative Commons Attribution-NonCommercial-ShareAlike 4.0 International License. To view a copy of this license, visit http://creativecommons.org/licenses/by-nc-sa/4.0/.

## Phase 1
Functional Requirements
Phase 1 – Cleaning, Clearing and Flow Improvement

Requirement Numbers		Requirement	Priority	Type	Status
Source	Derived
2.1.1		Maintain a water flow in the river system at all times; sufficient to ensure water clarity and inhibit algae growth.	1	Essential	In progress
1.2	1.1	The Project shall remove obstructions to water flow in the river.	1	Essential	Complete
1.3	1.2	The Project shall remove obstructions to water flow in the plumbing system.	1	Essential	Complete
1.3	1.3	The Project shall provide a more powerful, more efficient, variable speed pump.	1	Essential	Complete
2.1.2		Reduce the dependence of the river system on mains water.	1	Essential	In progress
1.1	1.4	The system shall maintain the integrity of the river bed by stopping all identifiable leaks.	1	Essential	Complete 1

Notes:	1	This Requirement has essentially been fulfilled, but it is recognised that it is an ongoing maintenance task which will require attention at least every Winter.

## Phase 2
Functional Requirements
Phase 2 – Improve Water Clarity and the WMT as a Visitor Attraction

Requirement Numbers		Requirement	Priority	Type	Status
Source	Derived
2.1.1		Maintain a water flow in the river system at all times; sufficient to ensure water clarity and inhibit algae growth.	1	Essential	In progress
2.1	2.1	The system shall provide a filter cage at the inlet of the pump to prevent large debris from being drawn into the pump impeller.	1	Essential	Complete
2.2	2.2	The system shall provide a natural water filtration system in the form of a bog garden to mechanically and biologically condition the water passing through it.	1	Essential	Complete
2.3	2.3	The system shall provide a pre-sump filter to prevent large debris from reaching the pump impeller inlet filter.	1	Essential	In progress
2.1.3		Enhance WMT as a Visitor Attraction.	1	Essential	In progress1
2.2	2.4	A variety of suitable plants shall be planted in the bog garden to create a new eco-system.	1	Essential	In progress
2.2	2.4.1	The locations of all plants shall be documented.	1	Essential	In progress

Notes:	1	This requirement appears in multiple places (also in Phase 4) yet isn’t specified precisely. Does this requirement include enhancing WMT’s educational value?

## Phase 3
Functional Requirements
Phase 3 – Reduce the Dependence of the River System on Mains Water

Requirement Numbers		Requirement	Priority	Type	Status
Source	Derived
2.1.2		Reduce the dependence of the river system on mains water.	1	Essential	In progress
3.2	3.1	Water butts shall be provided to store excess water from the river, so that the level may be replenished as necessary.	1	Essential	In progress
3.1	3.1.1	The necessary piping shall be provided between the water butts and the river.	1	Essential	In progress
3.3	3.1.2	A method of transferring water from the sump to the butts shall be provided. 1	1	Essential	In progress
3.3	3.1.3	A stop-tap shall be provided to control the flow of water from the butts to the river.	1	Essential	In progress
3.3	3.1.4	An overflow facility shall be provided for each butt.	2	Desirable	Not started

Notes:	1	If practicable, the existing sump pump should be re-used for this purpose.

## Phase 4
Functional Requirements
Phase 4 – Automate the System

Requirement Numbers		Requirement	Priority	Type	Status
Source	Derived
2.1.1		Maintain a water flow in the river system at all times; sufficient to ensure water clarity and inhibit algae growth.	1	Essential	In progress
4.1	4.1	Capture Requirement for the Phase.	2	Desirable	This document
4.2	4.2	Develop high level design for the system.	2	Desirable	Not started
4.3	4.3	The system shall provide a fully automated control for all aspects of the river system.	2	Desirable	Not started
4.3	4.3.1	Automated control of the system shall utilise embedded computer techniques.	2	Desirable	Not started
4.3	4.3.1.1	The system shall allow for manual (hardware) override of the controlling functions.	2	Desirable	Not started
	4.3.1.2	A test mode shall be provided.	2	Desirable	Not Started
4.3	4.3.1.3	A Graphical User Interface (GUI) shall be provided.	2	Desirable	Not started
4.3	4.3.1.3.1	The GUI shall provide a user-friendly status readout as well as some basic monitoring on its main window.	2	Essential	Not Started
4.3	4.3.1.3.2	The GUI shall have all of its features presented in one tabbed window for ease of use.	2	Desirable	Not Started
4.3	4.3.1.3.3	The GUI shall offer software manual override features on its main window for use in the event of a software failure.	2	Essential	Not Started
4.3	4.3.1.3.4	The GUI will be controllable via a PC in the main building and/or directly at the location of the embedded system.	2	Essential	Not Started
2.1.3		Enhance WMT as a Visitor Attraction.	2	Essential	Not started
	4.4	Educational displays shall be provided to inform visitors.	2	Desirable	Not started
4.4	4.4.1	A functional overview diagram of how the river control system works/will work shall be provided.	2	Desirable	Not Started
4.4	4.4.2	Sensor outputs such as flow metres and depth levels shall be displayed for visitors to see.	3	Desirable	Not Started

## Phase 5
Functional Requirements
Phase 5 – Expand Rainwater Storage and Irrigation

Requirement Numbers		Requirement	Priority	Type	Status
Source	Derived
2.2.2		Expand rain water harvesting, storage and irrigation feeds to suit needs of river / gardens.	2	Desirable	Not started
-	5.1	Flexible hoses and ‘soaker’ hoses shall be provided to allow gardeners to irrigate plants.	2	Desirable	In progress
-	5.1.1	A means of controlling the flow of water to the soaker hoses shall be provided.	2	Desirable	Not started
5.1.1	5.1.1.1	Initially, a physical control system shall be implemented.	2	Essential	Not Started
5.1.1	5.1.1.2	When convenient, an automated software control system shall be implemented.	2	Desirable	Not Started
5.1.1.2	5.1.1.2.1	The automated control system must have an emergency shut-off feature.	2	Essential	Not Started

## Phase 6
Functional Requirements
Phase 6 – Stored Water Balancing Between Storage Sites

Requirement Numbers		Requirement	Priority	Type	Status
Source	Derived
2.2.3		Stored water “balancing” between storage sites.	2	Desirable	Not started
-	6.1	Additional rainwater butts shall be located in suitable places to harvest water from the roofs of the WMT buildings.	2	Desirable	Not started
6.1	6.1.1	These rainwater butts shall be connected to the existing river control system.	2	Desirable	Not Started
-	6.1.1	A means of balancing the water levels in the rainwater butts shall be provided.	2	Desirable	Not started