## Sheet 1
Table 1
| Phase.Step | Status
| 1.1 | Complete
| 1.2 | Complete
| 1.3 | Complete
| 2.1 | Complete
| 2.2 | Complete
| 2.3 | Filter cages obtained but not yet fitted
| 3.1 | Complete. The pipes are in the ground and available for use but neither end is connected to anything yet. We’ve laid 5off 20mm flexible pipes with the intention that 4 would be used for water transfer, 2 for water flowing sump to butts and 2 for the other direction. The fifth pipe is for routing electrical cables. There was some 20mm pipe lying around at WMT, that’s why it was used. With some clever plumbing we could get all 4 water pipes carrying water in either direction, I'm sure, but I haven’t given it too much thought, yet. How much flow do we need?, I don’t know; the main (variable speed pump) can theoretically shift between 5,000 and 15,000 litres per hour, so at full speed it could empty the sump in less than 2 minutes!
| 3.2 | Water butts obtained and work has begun to prepare locations for their installation. The major part of the required pipework has been obtained but we haven't started connecting things up first.
| 3.3 | We have the pump (not convinced of it’s suitability but should do to get us going) and the tap but need 3.2 completed before we continue.
4.1
4.2
| 4.3 | I have the driver hardware for the variable speed pump.
4.4
| 5 | We have the soaker hoses
6